## Data Backup (hidden)
FIELD'S EXPLANATION
Sprint | Sprint Number
Hours | Hours that the team is available to develop in this sprint
Planned Issues | Number of Issues or tasks that the team has planned to do in this sprint
Planned SP | Total of the Story Points the team has commited to do in this sprint.
Planned Issues Done | Number of issues done that were planned
Unplanned Issues Done | Number of issues done that were NOT planned
Bugs | Total Amount of bug issues done during this sprint (planned or unplanned)
Total Issues Done | Total amount of issues done during this sprint
Planned Issues NOT Done | Total amount of issues planned that were NOT done
% Planned Issues | % of planned issues done in this sprint
% Unplanned Issues | % of unplanned issues done in this sprint
Planned SP Done | Number of Story Points Done that were planned
Unplanned SP Done | Number of Story Points Done that were NOT planned
Bugs (SP) | SP of bugs done during this sprint (planned or unplanned)
Total SP Done | Total amount of Story Points done during this sprint
Planned SP NOT Done | Total amount of Story Points planned that were NOT done
% Planned SP | % of planned story points done in this sprint
% Unplanned SP | % of unplanned story points done in this sprint
% Compliance | % compliance with what was planned: SP Done / Sp Planned
Ratio SP / issue | Story Points per issue ratio
SP / Hours | Team effectiveness in terms of value delivery per hour worked
Hours Next Sprint | Estimation of team avaliability hours for next sprint
Estimated Total SP | Used to plan next sprint. SP that should be for next sprint regarding average delivery of the previous 5 sprints and team capacity
Estimated SP Planned | Used to plan next sprint. SP that should be planned for next sprint regarding estimated total SP minus possible unplanned work
Estimated SP Unplanned | Used to plan next sprint. Unplanned SP that the team would have next sprint regarding average of unplanned SP for the previous 5 sprints
Estimated % Compliance | % of estimated team compliance taking in account the average of the previous 5 sprints
Compliance final % var | % of compliance final variation on what was predicted and what finally was
Sprint | Hours | Planned Issues | Planned SP | Planned Issues Done | Unplanned Issues Done | Bugs (Issues) | Total Issues Done | Planned Issues NOT Done | % Planned Issues | % Unplanned Issues | Planned SP Done | Unplanned SP Done | Bugs (SP) | Total SP Done | Planned SP NOT Done | % Planned SP | % Unplanned SP | % Compliance | Ratio SP / issue | SP / Hours | Hours Next Sprint | Estimated Total SP | Estimated SP Planned | Estimated SP Unplanned | Estimated % Compliance | Compliance final % var
41 | 535 | 16 | 104 | 10 | 7 | 0 | 17 | 6 | 58.82% | 41.18% | 63 | 28 | 0 | 91 | 41 | 69.23% | 30.77% | 60.58% | -4.3529 | 0.17009 | 513 | 88 | 60 | 28 | 60.58% | -1.318%
42 | 513 | 16 | 108 | 11 | 6 | 1 | 17 | 5 | 64.71% | 35.29% | 64 | 25 | 3 | 89 | 44 | 71.91% | 28.09% | 59.26% | 5.2353 | 0.17349 | 374 | 65 | 45 | 20 | 59.92% | -3.668%
43 | 374 | 12 | 80 | 11 | 6 | 2 | 17 | 1 | 64.71% | 35.29% | 45 | 22 | 5 | 67 | 35 | 67.16% | 32.84% | 56.25% | 3.9412 | 0.17914 | 411 | 72 | 49 | 23 | 58.7% | -4.763%
44 | 411 | 14 | 89 | 11 | 8 | 1 | 19 | 3 | 57.89% | 42.11% | 48 | 27 | 2 | 75 | 41 | 64% | 36% | 53.93% | 3.9474 | 0.18248 | 397 | 70 | 47 | 23 | 57.5% | 4.601%
45 | 397 | 14 | 95 | 12 | 5 | 3 | 17 | 2 | 70.59% | 29.41% | 59 | 15 | 6 | 74 | 36 | 79.73% | 20.27% | 62.11% | 4.3529 | 0.1864 | 437 | 78 | 54 | 24 | 58.42% | 7.902%
46 | 437 | 16 | 98 | 8 | 4 | 1 | 12 | 8 | 66.67% | 33.33% | 65 | 19 | 8 | 84 | 33 | 77.38% | 22.62% | 66.33% | 7 | 0.19222 | 435 | 79 | 56 | 23 | 59.74% | 3.651%
47 | 435 | 17 | 112 | 12 | 4 | 2 | 16 | 5 | 75% | 25% | 71 | 14 | 3 | 85 | 41 | 83.53% | 16.47% | 63.39% | 5.3125 | 0.1954 | 334 | 72 | 52 | 20 | 60.26% | 10.47%
48 | 334 | 14 | 82 | 13 | 6 | 4 | 19 | 1 | 68.42% | 31.58% | 58 | 9 | 12 | 67 | 24 | 86.57% | 13.43% | 70.73% | 3.5263 | 0.2006 | 453 | 98 | 73 | 25 | 61.57% | 9.857%
49 | 453 | 19 | 105 | 8 | 8 | 5 | 16 | 11 | 50% | 50% | 75 | 17 | 12 | 92 | 30 | 81.52% | 18.48% | 71.43% | 5.75 | 0.20309 | 527 | 115 | 87 | 28 | 62.93% | 2.925%
50 | 527 | 23 | 123 | 16 | 4 | 5 | 20 | 7 | 80% | 20% | 81 | 29 | 15 | 110 | 42 | 73.64% | 26.36% | 65.85% | 5.5 | 0.20873 | 343 | 76 | 61 | 15 | 67.55% | -18.57%
51 | 343 | 16 | 98 | 10 | 5 | 3 | 15 | 6 | 66.67% | 33.33% | 48 | 25 | 14 | 73 | 50 | 65.75% | 34.25% | 48.98% | 4.8667 | 0.21283 | 399 | 89 | 69 | 20 | 64.08% | 2.589%
52 | 399 | 19 | 120 | 16 | 2 | 2 | 18 | 3 | 88.89% | 11.11% | 80 | 6 | 6 | 86 | 40 | 93.02% | 6.977% | 66.67% | 4.7778 | 0.21554 | 402 | 90 | 72 | 18 | 64.73% | 1.355%
53 | 402 | 20 | 115 | 17 | 3 | 4 | 20 | 3 | 85% | 15% | 76 | 13 | 8 | 89 | 39 | 85.39% | 14.61% | 66.09% | 4.45 | 0.22139 | 314 | 71 | 56 | 15 | 63.8% | 7.281%
54 | 314 | 16 | 83 | 14 | 4 | 6 | 18 | 2 | 77.78% | 22.22% | 59 | 12 | 8 | 71 | 24 | 83.1% | 16.9% | 71.08% | 3.9444 | 0.22611 | 520 | 118 | 94 | 24 | 63.73% | 31.59%
55 | 520 | 21 | 107 | 18 | 3 | 4 | 21 | 3 | 85.71% | 14.29% | 102 | 17 | 12 | 119 | 5 | 85.71% | 14.29% | 95.33% | 5.6667 | 0.22885 | 535 | 121 | 99 | 22 | 69.63% | 24.49%
56 | 535 | 23 | 102 | 20 | 4 | 1 | 24 | 3 | 83.33% | 16.67% | 96 | 23 | 5 | 119 | 6 | 80.67% | 19.33% | 94.12% | 4.9583 | 0.22243 | 378 | 85 | 68 | 17 | 94.12% | 4.617%
57 | 378 | 19 | 79 | 16 | 2 | 4 | 18 | 3 | 88.89% | 11.11% | 78 | 23 | 12 | 101 | 1 | 77.23% | 22.77% | 98.73% | 5.6111 | 0.2672 | 311 | 77 | 60 | 17 | 96.43% | -13.31%
58 | 311 | 14 | 77 | 9 | 2 | 1 | 11 | 5 | 81.82% | 18.18% | 64 | 28 | 3 | 92 | 13 | 69.57% | 30.43% | 83.12% | 8.3636 | 0.29582 | 549 | 144 | 109 | 35 | 91.99% | 0.2434%
59 | 549 | 21 | 103 | 15 | 7 | 5 | 22 | 6 | 68.18% | 31.82% | 95 | 23 | 10 | 118 | 8 | 80.51% | 19.49% | 92.23% | 5.3636 | 0.21494 | 522 | 131 | 100 | 31 | 92.05% | -23.02%
60 | 522 | 21 | 113 | 12 | 4 | 2 | 16 | 9 | 75% | 25% | 78 | 21 | 8 | 99 | 35 | 78.79% | 21.21% | 69.03% | 6.1875 | 0.18966 | 515 | 123 | 95 | 28 | 87.45% | -2.887%
61 | 515 | 26 | 136 | 21 | 5 | 3 | 26 | 5 | 80.77% | 19.23% | 115 | 22 | 7 | 137 | 21 | 83.94% | 16.06% | 84.56% | 5.2692 | 0.26602 | 449 | 109 | 85 | 24 | 86.96% | -22.68%
62 | 449 | 19 | 84 | 10 | 3 | 2 | 13 | 9 | 76.92% | 23.08% | 54 | 9 | 5 | 63 | 30 | 85.71% | 14.29% | 64.29% | 4.8462 | 0.14031 | 509 | 117 | 92 | 25 | 81.99% | 7.238%
63 | 509 | 18 | 65 | 6 | 4 | 1 | 10 | 12 | 60% | 40% | 58 | 14 | 3 | 72 | 7 | 80.56% | 19.44% | 89.23% | 7.2 | 0.14145 | 394 | 86 | 68 | 18 | 80.41% | 10.82%
64 | 394 | 13 | 57 | 12 | 3 | 1 | 15 | 1 | 80% | 20% | 52 | 9 | 6 | 61 | 5 | 85.25% | 14.75% | 91.23% | 4.0667 | 0.15482 | 431 | 91 | 75 | 16 | 81.76% | 3.314%
65 | 431 | 17 | 67 | 8 | 2 | 3 | 10 | 9 | 80% | 20% | 57 | 6 | 5 | 63 | 10 | 90.48% | 9.524% | 85.07% | 6.3 | 0.14617 | 364 | 75 | 63 | 12 | 80.57% | 12.88%
66 | 364 | 11 | 61 | 5 | 2 | 2 | 7 | 6 | 71.43% | 28.57% | 57 | 4 | 6 | 61 | 4 | 93.44% | 6.557% | 93.44% | 8.7143 | 0.16758 | 448 | 90 | 77 | 13 | 84.64% | -84.64%

## PivotTables Backup (hidden)
Etiquetas de fila | Commited | Completed | Unplanned | Etiquetas de fila | Commited | Completed | Unplanned | Suma de Bugs (Issues) | Promedio de Bugs (Issues) | Promedio de % Compliance | Promedio de % Unplanned Issues | Etiquetas de fila | Planned | Unplanned | Etiquetas de fila | Planned | Unplanned | Promedio de % Unplanned SP | Promedio de Ratio SP / issue | Promedio de Hours | Promedio de Total Issues Done | Promedio de Planned Issues | Promedio de Planned SP | Promedio de Unplanned Issues Done | Promedio de Total SP Done | Promedio de Unplanned SP Done | Valores |  | Valores |  | Etiquetas de fila | Suma de Hours Next Sprint | Total SP | SP Planned | Promedio de Estimated SP Unplanned | % Estimated Compliance | Etiquetas de fila | Suma de Bugs (Issues) | Etiquetas de fila | Suma de % Compliance
43 | 12 | 17 | 6 | 43 | 80 | 67 | 22 | 53 | 3.1176 | 72.14% | 25.91% | 43 | 11 | 6 | 43 | 45 | 22 | 21.5% | 5.1372 | 418.7647 | 17.8235 | 17.5294 | 98.1176 | 4.5294 | 89.5294 | 18.9412 | Planned | 74.09% | Planned | 78.5% | 43 | 411 | 72 | 49 | 23 | 58.7% | 43 | 2 | 43 | 56.25%
44 | 14 | 19 | 8 | 44 | 89 | 75 | 27 |  |  |  |  | 44 | 11 | 8 | 44 | 48 | 27 | [9 empty] | Unplanned | 25.91% | Unplanned | 21.5% | 44 | 397 | 70 | 47 | 23 | 57.5% | 44 | 1 | 44 | 53.93%
45 | 14 | 17 | 5 | 45 | 95 | 74 | 15 |  |  |  |  | 45 | 12 | 5 | 45 | 59 | 15 | [13 empty] | 45 | 437 | 78 | 54 | 24 | 58.42% | 45 | 3 | 45 | 62.11%
46 | 16 | 12 | 4 | 46 | 98 | 84 | 19 |  |  |  |  | 46 | 8 | 4 | 46 | 65 | 19 | [13 empty] | 46 | 435 | 79 | 56 | 23 | 59.74% | 46 | 1 | 46 | 66.33%
47 | 17 | 16 | 4 | 47 | 112 | 85 | 14 |  |  |  |  | 47 | 12 | 4 | 47 | 71 | 14 | [13 empty] | 47 | 334 | 72 | 52 | 20 | 60.26% | 47 | 2 | 47 | 63.39%
48 | 14 | 19 | 6 | 48 | 82 | 67 | 9 |  |  |  |  | 48 | 13 | 6 | 48 | 58 | 9 | [13 empty] | 48 | 453 | 98 | 73 | 25 | 61.57% | 48 | 4 | 48 | 70.73%
49 | 19 | 16 | 8 | 49 | 105 | 92 | 17 |  |  |  |  | 49 | 8 | 8 | 49 | 75 | 17 | [13 empty] | 49 | 527 | 115 | 87 | 28 | 62.93% | 49 | 5 | 49 | 71.43%
50 | 23 | 20 | 4 | 50 | 123 | 110 | 29 |  |  |  |  | 50 | 16 | 4 | 50 | 81 | 29 | [13 empty] | 50 | 343 | 76 | 61 | 15 | 67.55% | 50 | 5 | 50 | 65.85%
51 | 16 | 15 | 5 | 51 | 98 | 73 | 25 |  |  |  |  | 51 | 10 | 5 | 51 | 48 | 25 | [13 empty] | 51 | 399 | 89 | 69 | 20 | 64.08% | 51 | 3 | 51 | 48.98%
52 | 19 | 18 | 2 | 52 | 120 | 86 | 6 |  |  |  |  | 52 | 16 | 2 | 52 | 80 | 6 | [13 empty] | 52 | 402 | 90 | 72 | 18 | 64.73% | 52 | 2 | 52 | 66.67%
53 | 20 | 20 | 3 | 53 | 115 | 89 | 13 |  |  |  |  | 53 | 17 | 3 | 53 | 76 | 13 | [13 empty] | 53 | 314 | 71 | 56 | 15 | 63.8% | 53 | 4 | 53 | 66.09%
54 | 16 | 18 | 4 | 54 | 83 | 71 | 12 |  |  |  |  | 54 | 14 | 4 | 54 | 59 | 12 | [13 empty] | 54 | 520 | 118 | 94 | 24 | 63.73% | 54 | 6 | 54 | 71.08%
55 | 21 | 21 | 3 | 55 | 107 | 119 | 17 |  |  |  |  | 55 | 18 | 3 | 55 | 102 | 17 | [13 empty] | 55 | 535 | 121 | 99 | 22 | 69.63% | 55 | 4 | 55 | 95.33%
56 | 23 | 24 | 4 | 56 | 102 | 119 | 23 |  |  |  |  | 56 | 20 | 4 | 56 | 96 | 23 | [13 empty] | 56 | 378 | 85 | 68 | 17 | 94.12% | 56 | 1 | 56 | 94.12%
57 | 19 | 18 | 2 | 57 | 79 | 101 | 23 |  |  |  |  | 57 | 16 | 2 | 57 | 78 | 23 | [13 empty] | 57 | 311 | 77 | 60 | 17 | 96.43% | 57 | 4 | 57 | 98.73%
58 | 14 | 11 | 2 | 58 | 77 | 92 | 28 |  |  |  |  | 58 | 9 | 2 | 58 | 64 | 28 | [13 empty] | 58 | 549 | 144 | 109 | 35 | 91.99% | 58 | 1 | 58 | 83.12%
59 | 21 | 22 | 7 | 59 | 103 | 118 | 23 |  |  |  |  | 59 | 15 | 7 | 59 | 95 | 23 | [13 empty] | 59 | 522 | 131 | 100 | 31 | 92.05% | 59 | 5 | 59 | 92.23%
Total general | 298 | 303 | 77 | Total general | 1668 | 1522 | 322 |  |  |  |  | Total general | 226 | 77 | Total general | 1200 | 322 | [19 empty] | Total general | 53 | Total general | 12.2637
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.

## Dashboard Backup (hidden)
Sprint | Team Availability (hours) | Estimated Story Points | Estimated Unplanned SP | SP that should be planned | Estimated compliance
66 | 448 | 90 | 13 | 77 | 84.64%
Scrum Master Control Dashboard
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Estimations for next Sprint Planning
ISSUES
STORY POINTS

## Data
Sprint | Hours | Planned Issues | Planned SP | Planned Issues Done | Unplanned Issues Done | Bugs (Issues) | Total Issues Done | Planned Issues NOT Done | % Planned Issues | % Unplanned Issues | Planned SP Done | Unplanned SP Done | Bugs (SP) | Total SP Done | Planned SP NOT Done | % Planned SP | % Unplanned SP | % Compliance | Ratio SP / issue | SP / Hours | Hours Next Sprint | Estimated Total SP | Estimated SP Planned | Estimated SP Unplanned | Estimated % Compliance | Compliance final % var
41 | 535 | 16 | 104 | 10 | 7 | 0 | 17 | 6 | 58.82% | 41.18% | 63 | 28 | 0 | 91 | 41 | 69.23% | 30.77% | 60.58% | -4.3529 | 0.17009 | 513 | 88 | 60 | 28 | 60.58% | -1.318%
42 | 513 | 16 | 108 | 11 | 6 | 1 | 17 | 5 | 64.71% | 35.29% | 64 | 25 | 3 | 89 | 44 | 71.91% | 28.09% | 59.26% | 5.2353 | 0.17349 | 374 | 65 | 45 | 20 | 59.92% | -3.668%
43 | 374 | 12 | 80 | 11 | 6 | 2 | 17 | 1 | 64.71% | 35.29% | 45 | 22 | 5 | 67 | 35 | 67.16% | 32.84% | 56.25% | 3.9412 | 0.17914 | 411 | 72 | 49 | 23 | 58.7% | -4.763%
44 | 411 | 14 | 89 | 11 | 8 | 1 | 19 | 3 | 57.89% | 42.11% | 48 | 27 | 2 | 75 | 41 | 64% | 36% | 53.93% | 3.9474 | 0.18248 | 397 | 70 | 47 | 23 | 57.5% | 4.601%
45 | 397 | 14 | 95 | 12 | 5 | 3 | 17 | 2 | 70.59% | 29.41% | 59 | 15 | 6 | 74 | 36 | 79.73% | 20.27% | 62.11% | 4.3529 | 0.1864 | 437 | 78 | 54 | 24 | 58.42% | 7.902%
46 | 437 | 16 | 98 | 8 | 4 | 1 | 12 | 8 | 66.67% | 33.33% | 65 | 19 | 8 | 84 | 33 | 77.38% | 22.62% | 66.33% | 7 | 0.19222 | 435 | 79 | 56 | 23 | 59.74% | 3.651%
47 | 435 | 17 | 112 | 12 | 4 | 2 | 16 | 5 | 75% | 25% | 71 | 14 | 3 | 85 | 41 | 83.53% | 16.47% | 63.39% | 5.3125 | 0.1954 | 334 | 72 | 52 | 20 | 60.26% | 10.47%
48 | 334 | 14 | 82 | 13 | 6 | 4 | 19 | 1 | 68.42% | 31.58% | 58 | 9 | 12 | 67 | 24 | 86.57% | 13.43% | 70.73% | 3.5263 | 0.2006 | 453 | 98 | 73 | 25 | 61.57% | 9.857%
49 | 453 | 19 | 105 | 8 | 8 | 5 | 16 | 11 | 50% | 50% | 75 | 17 | 12 | 92 | 30 | 81.52% | 18.48% | 71.43% | 5.75 | 0.20309 | 527 | 115 | 87 | 28 | 62.93% | 2.925%
50 | 527 | 23 | 123 | 16 | 4 | 5 | 20 | 7 | 80% | 20% | 81 | 29 | 15 | 110 | 42 | 73.64% | 26.36% | 65.85% | 5.5 | 0.20873 | 343 | 76 | 61 | 15 | 67.55% | -18.57%
51 | 343 | 16 | 98 | 10 | 5 | 3 | 15 | 6 | 66.67% | 33.33% | 48 | 25 | 14 | 73 | 50 | 65.75% | 34.25% | 48.98% | 4.8667 | 0.21283 | 399 | 89 | 69 | 20 | 64.08% | 2.589%
52 | 399 | 19 | 120 | 16 | 2 | 2 | 18 | 3 | 88.89% | 11.11% | 80 | 6 | 6 | 86 | 40 | 93.02% | 6.977% | 66.67% | 4.7778 | 0.21554 | 402 | 90 | 72 | 18 | 64.73% | 1.355%
53 | 402 | 20 | 115 | 17 | 3 | 4 | 20 | 3 | 85% | 15% | 76 | 13 | 8 | 89 | 39 | 85.39% | 14.61% | 66.09% | 4.45 | 0.22139 | 314 | 71 | 56 | 15 | 63.8% | 7.281%
54 | 314 | 16 | 83 | 14 | 4 | 6 | 18 | 2 | 77.78% | 22.22% | 59 | 12 | 8 | 71 | 24 | 83.1% | 16.9% | 71.08% | 3.9444 | 0.22611 | 520 | 118 | 94 | 24 | 63.73% | 31.59%
55 | 520 | 21 | 107 | 18 | 3 | 4 | 21 | 3 | 85.71% | 14.29% | 102 | 17 | 12 | 119 | 5 | 85.71% | 14.29% | 95.33% | 5.6667 | 0.22885 | 535 | 121 | 99 | 22 | 69.63% | 24.49%
56 | 535 | 23 | 102 | 20 | 4 | 1 | 24 | 3 | 83.33% | 16.67% | 96 | 23 | 5 | 119 | 6 | 80.67% | 19.33% | 94.12% | 4.9583 | 0.22243 | 378 | 85 | 68 | 17 | 94.12% | 4.617%
57 | 378 | 19 | 79 | 16 | 2 | 4 | 18 | 3 | 88.89% | 11.11% | 78 | 23 | 12 | 101 | 1 | 77.23% | 22.77% | 98.73% | 5.6111 | 0.2672 | 311 | 77 | 60 | 17 | 96.43% | -13.31%
58 | 311 | 14 | 77 | 9 | 2 | 1 | 11 | 5 | 81.82% | 18.18% | 64 | 28 | 3 | 92 | 13 | 69.57% | 30.43% | 83.12% | 8.3636 | 0.29582 | 549 | 144 | 109 | 35 | 91.99% | 0.2434%
59 | 549 | 21 | 103 | 15 | 7 | 5 | 22 | 6 | 68.18% | 31.82% | 95 | 23 | 10 | 118 | 8 | 80.51% | 19.49% | 92.23% | 5.3636 | 0.21494 | 522 | 131 | 100 | 31 | 92.05% | -23.02%
60 | 522 | 21 | 113 | 12 | 4 | 2 | 16 | 9 | 75% | 25% | 78 | 21 | 8 | 99 | 35 | 78.79% | 21.21% | 69.03% | 6.1875 | 0.18966 | 515 | 123 | 95 | 28 | 87.45% | -2.887%
61 | 515 | 26 | 136 | 21 | 5 | 3 | 26 | 5 | 80.77% | 19.23% | 115 | 22 | 7 | 137 | 21 | 83.94% | 16.06% | 84.56% | 5.2692 | 0.26602 | 449 | 109 | 85 | 24 | 86.96% | -22.68%
62 | 449 | 19 | 84 | 10 | 3 | 2 | 13 | 9 | 76.92% | 23.08% | 54 | 9 | 5 | 63 | 30 | 85.71% | 14.29% | 64.29% | 4.8462 | 0.14031 | 509 | 117 | 92 | 25 | 81.99% | 7.238%
63 | 509 | 18 | 65 | 6 | 4 | 1 | 10 | 12 | 60% | 40% | 58 | 14 | 3 | 72 | 7 | 80.56% | 19.44% | 89.23% | 7.2 | 0.14145 | 394 | 86 | 68 | 18 | 80.41% | 10.82%
64 | 394 | 13 | 57 | 12 | 3 | 1 | 15 | 1 | 80% | 20% | 52 | 9 | 6 | 61 | 5 | 85.25% | 14.75% | 91.23% | 4.0667 | 0.15482 | 431 | 91 | 75 | 16 | 81.76% | 3.314%
65 | 431 | 17 | 67 | 8 | 2 | 3 | 10 | 9 | 80% | 20% | 57 | 6 | 5 | 63 | 10 | 90.48% | 9.524% | 85.07% | 6.3 | 0.14617 | 364 | 75 | 63 | 12 | 80.57% | 12.88%
66 | 364 | 11 | 61 | 5 | 2 | 2 | 7 | 6 | 71.43% | 28.57% | 57 | 4 | 6 | 61 | 4 | 93.44% | 6.557% | 93.44% | 8.7143 | 0.16758 | 448 | 90 | 77 | 13 | 84.64% | -84.64%

## PivotTables
Etiquetas de fila | Commited | Completed | Unplanned | Etiquetas de fila | Commited | Completed | Unplanned | Suma de Bugs (Issues) | Promedio de Bugs (Issues) | Promedio de % Compliance | Promedio de % Unplanned Issues | Etiquetas de fila | Planned | Unplanned | Etiquetas de fila | Planned | Unplanned | Promedio de % Unplanned SP | Promedio de Ratio SP / issue | Promedio de Hours | Promedio de Total Issues Done | Promedio de Planned Issues | Promedio de Planned SP | Promedio de Unplanned Issues Done | Promedio de Total SP Done | Promedio de Unplanned SP Done | Valores |  | Valores |  | Etiquetas de fila | Suma de Hours Next Sprint | Total SP | SP Planned | Promedio de Estimated SP Unplanned | % Estimated Compliance | Etiquetas de fila | Suma de Bugs (Issues) | Etiquetas de fila | Suma de % Compliance
43 | 12 | 17 | 6 | 43 | 80 | 67 | 22 | 53 | 3.1176 | 72.14% | 25.91% | 43 | 11 | 6 | 43 | 45 | 22 | 21.5% | 5.1372 | 418.7647 | 17.8235 | 17.5294 | 98.1176 | 4.5294 | 89.5294 | 18.9412 | Planned | 74.09% | Planned | 78.5% | 43 | 411 | 72 | 49 | 23 | 58.7% | 43 | 2 | 43 | 56.25%
44 | 14 | 19 | 8 | 44 | 89 | 75 | 27 |  |  |  |  | 44 | 11 | 8 | 44 | 48 | 27 | [9 empty] | Unplanned | 25.91% | Unplanned | 21.5% | 44 | 397 | 70 | 47 | 23 | 57.5% | 44 | 1 | 44 | 53.93%
45 | 14 | 17 | 5 | 45 | 95 | 74 | 15 |  |  |  |  | 45 | 12 | 5 | 45 | 59 | 15 | [13 empty] | 45 | 437 | 78 | 54 | 24 | 58.42% | 45 | 3 | 45 | 62.11%
46 | 16 | 12 | 4 | 46 | 98 | 84 | 19 |  |  |  |  | 46 | 8 | 4 | 46 | 65 | 19 | [13 empty] | 46 | 435 | 79 | 56 | 23 | 59.74% | 46 | 1 | 46 | 66.33%
47 | 17 | 16 | 4 | 47 | 112 | 85 | 14 |  |  |  |  | 47 | 12 | 4 | 47 | 71 | 14 | [13 empty] | 47 | 334 | 72 | 52 | 20 | 60.26% | 47 | 2 | 47 | 63.39%
48 | 14 | 19 | 6 | 48 | 82 | 67 | 9 |  |  |  |  | 48 | 13 | 6 | 48 | 58 | 9 | [13 empty] | 48 | 453 | 98 | 73 | 25 | 61.57% | 48 | 4 | 48 | 70.73%
49 | 19 | 16 | 8 | 49 | 105 | 92 | 17 |  |  |  |  | 49 | 8 | 8 | 49 | 75 | 17 | [13 empty] | 49 | 527 | 115 | 87 | 28 | 62.93% | 49 | 5 | 49 | 71.43%
50 | 23 | 20 | 4 | 50 | 123 | 110 | 29 |  |  |  |  | 50 | 16 | 4 | 50 | 81 | 29 | [13 empty] | 50 | 343 | 76 | 61 | 15 | 67.55% | 50 | 5 | 50 | 65.85%
51 | 16 | 15 | 5 | 51 | 98 | 73 | 25 |  |  |  |  | 51 | 10 | 5 | 51 | 48 | 25 | [13 empty] | 51 | 399 | 89 | 69 | 20 | 64.08% | 51 | 3 | 51 | 48.98%
52 | 19 | 18 | 2 | 52 | 120 | 86 | 6 |  |  |  |  | 52 | 16 | 2 | 52 | 80 | 6 | [13 empty] | 52 | 402 | 90 | 72 | 18 | 64.73% | 52 | 2 | 52 | 66.67%
53 | 20 | 20 | 3 | 53 | 115 | 89 | 13 |  |  |  |  | 53 | 17 | 3 | 53 | 76 | 13 | [13 empty] | 53 | 314 | 71 | 56 | 15 | 63.8% | 53 | 4 | 53 | 66.09%
54 | 16 | 18 | 4 | 54 | 83 | 71 | 12 |  |  |  |  | 54 | 14 | 4 | 54 | 59 | 12 | [13 empty] | 54 | 520 | 118 | 94 | 24 | 63.73% | 54 | 6 | 54 | 71.08%
55 | 21 | 21 | 3 | 55 | 107 | 119 | 17 |  |  |  |  | 55 | 18 | 3 | 55 | 102 | 17 | [13 empty] | 55 | 535 | 121 | 99 | 22 | 69.63% | 55 | 4 | 55 | 95.33%
56 | 23 | 24 | 4 | 56 | 102 | 119 | 23 |  |  |  |  | 56 | 20 | 4 | 56 | 96 | 23 | [13 empty] | 56 | 378 | 85 | 68 | 17 | 94.12% | 56 | 1 | 56 | 94.12%
57 | 19 | 18 | 2 | 57 | 79 | 101 | 23 |  |  |  |  | 57 | 16 | 2 | 57 | 78 | 23 | [13 empty] | 57 | 311 | 77 | 60 | 17 | 96.43% | 57 | 4 | 57 | 98.73%
58 | 14 | 11 | 2 | 58 | 77 | 92 | 28 |  |  |  |  | 58 | 9 | 2 | 58 | 64 | 28 | [13 empty] | 58 | 549 | 144 | 109 | 35 | 91.99% | 58 | 1 | 58 | 83.12%
59 | 21 | 22 | 7 | 59 | 103 | 118 | 23 |  |  |  |  | 59 | 15 | 7 | 59 | 95 | 23 | [13 empty] | 59 | 522 | 131 | 100 | 31 | 92.05% | 59 | 5 | 59 | 92.23%
Total general | 298 | 303 | 77 | Total general | 1668 | 1522 | 322 |  |  |  |  | Total general | 226 | 77 | Total general | 1200 | 322 | [19 empty] | Total general | 53 | Total general | 12.2637
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.

## Dashboard
Sprint | Team Availability (hours) | Estimated Story Points | Estimated Unplanned SP | SP that should be planned | Estimated compliance
66 | 448 | 90 | 13 | 77 | 84.64%
Scrum Master Control Dashboard
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Estimations for next Sprint Planning
ISSUES
STORY POINTS